## Sheet1
Case: Case Number | Account Name | Case: Case Record Type | Project Milestone: Project Milestone Name | Milestone Order | Start Date | Predecessor Name | Latest Estimated Install | Latest Actual Install | Latest Estimated Activation | Latest Requested Ship | Completed On | Expected Completion | Owner Name | Milestone Status | Ready to Start | Started On | Verify Request | Additional T&M Currency | Additional T&M | T&M Description | Survey Dispatched | Survey Date | Survey Results | PO Received | Antennas Needed | Antenna Accessories | ABP Notes | Surveyed Reviewed | TV Server | Pro:Centric Remotes | Taps/Terminations | Jumpers | FMA Rental | Survey Discussed | Install Started | Programming Activated | Service Start Entered | Test Map | Mapping/Training | System Online | On Dashboard | MFH Overlay | Installer Released | Return Trip | As-Builts | Comp Docs Received | Closeout 1 | Closeout 2 | Closeout Response | Old Equip Deactivated | RM Completed | Post Install Issues | SHI Completed | PM Review
246116 | Doubletree Tucson Reid Park | COMM Install | Sale Verification - Comm | 1 | 2019-08-05 |  | 2019-10-03 |  |  | 2019-09-26 | 2019-08-05 |  | Undar Griffith-Mars | Completed | 2019-08-05 | 2019-08-05 | 2019-08-05 | USD | 0 | [25 empty] | 0 | [7 empty] | 0
246116 | Doubletree Tucson Reid Park | COMM Install | System Ordering - Comm | 3 |  | Intro Call - Comm | 2019-10-03 |  |  | 2019-09-26 | 2019-09-03 |  | Gregory Zwickl | Completed | 2019-08-08 |  |  | USD | 0 |  |  |  |  | 2019-09-03 | AU9 | NPRM | 12 H25 PV | Yes | [5 empty] | Yes | [10 empty] | 0 | [7 empty] | 0
246116 | Doubletree Tucson Reid Park | COMM Install | PM Review - Comm | 5 |  | Installation - Comm | 2019-10-03 |  |  | 2019-09-26 |  |  | Gregory Zwickl | Pending |  |  |  | USD | 0 | [25 empty] | 0 | [7 empty] | 0
246116 | Doubletree Tucson Reid Park | COMM Install | Installation - Comm | 4 |  | System Ordering - Comm | 2019-10-03 |  |  | 2019-09-26 |  |  | Jason Brosnick | New | 2019-09-03 |  |  | USD | 0 | [15 empty] | 2019-10-03 | 2019-10-03 | [8 empty] | 0 | [7 empty] | 0
246116 | Doubletree Tucson Reid Park | COMM Install | Intro Call - Comm | 2 |  | Sale Verification - Comm | 2019-10-03 |  |  | 2019-09-26 | 2019-08-08 |  | Alec Hammaker | Completed | 2019-08-05 |  |  | USD | 0 |  | 2019-08-05 | 2019-08-06 | 2019-08-08 | [21 empty] | 0 | [7 empty] | 0
246116 | Doubletree Tucson Reid Park | COMM Install | P&L | 6 |  |  | 2019-10-03 |  |  | 2019-09-26 |  |  | Mark Dixon | New | 2019-08-05 |  |  | USD | 0 | [25 empty] | 0 | [7 empty] | 0

## Sheet2
Name | Project Name | Status | Insert Before | Constraint Type | Start Date | Predecessor Sublist: Task | Predecessor Sublist: Type | Latest Estimated Install | Latest Actual Install | Latest Estimated Activation | Latest Requested Ship | Completed On | Expected Completion | Task Owner | Task Status | Ready to Start | Started On | Task Length in Days | PJ Task Subtab Link | Verify Request - COMM | Additional T&M - COMM | T&M Description - COMM | Survey Dispatched - COMM | Survey Date - COMM | Survey Results - COMM | PO Received - COMM | Antennas Needed - COMM | Antenna Accessories - COMM | ABP Notes - COMM | Survey Reviewed - COMM | TV Server - COMM | Pro:Centric Remotes - COMM | Taps/Terminations - COMM | Jumpers - COMM | FMA Rental - COMM | Survey Discussed - COMM | Install Started - COMM | Programming Activated - COMM | Service Start Entered - COMM | Test Map - COMM | Mapping/Training - COMM | System Online - COMM | On Dashboard - COMM | MFH Overlay - COMM | Installer Release Date - COMM | Return Trip - COMM | As-Builts - COMM | Comp Docs Received - COMM | Closeout 1 - COMM | Closeout 2 - COMM | Closeout Response - COMM | Old Equip Deactivated - COMM | RM Completed - COMM | Post Install Issues - COMM | SHI Completed - COMM | PM Review - COMM | Programming Activated - P&L Review - COMM
Sales Verification - COMM | 246116 - Doubletree Tucson Reid Park - COMM Install | Not Started | Intro Call - COMM |  | 2019-08-05 |  |  | 2019-10-03 |  |  | 2019-09-26 | 2019-08-05 |  | Undar Griffith-Mars | Completed | 2019-08-05 | 2019-08-05 | 0 | Sales Verification - COMM | 2019-08-05 | 0
System Ordering - COMM | 246116 - Doubletree Tucson Reid Park - COMM Install | Not Started | Installation - COMM |  |  | Intro Call - COMM |  | 2019-10-03 |  |  | 2019-09-26 | 2019-09-03 |  | Gregory Zwickl | Completed | 2019-08-08 |  | 26 | System Ordering - COMM | [6 empty] | 2019-09-03 | AU9 | NPRM | 12 H25 PV | Yes | [5 empty] | Yes
PM Review - COMM | 246116 - Doubletree Tucson Reid Park - COMM Install | Not Started | P&L Review - COMM |  |  | Installation - COMM |  | 2019-10-03 |  |  | 2019-09-26 |  |  | Gregory Zwickl | Pending |  |  | 0 | PM Review - COMM
Installation - COMM | 246116 - Doubletree Tucson Reid Park - COMM Install | Not Started | PM Review - COMM |  |  | System Ordering - COMM |  | 2019-10-03 |  |  | 2019-09-26 |  |  | Jason Brosnick | New | 2019-09-03 |  | 43 | Installation - COMM | [17 empty] | 2019-10-03 | 2019-10-03 | [8 empty] | 0 | [7 empty] | 0
Intro Call - COMM | 246116 - Doubletree Tucson Reid Park - COMM Install | Not Started | System Ordering - COMM |  |  | Sales Verification - COMM |  | 2019-10-03 |  |  | 2019-09-26 | 2019-08-08 |  | Alec Hammaker | Completed | 2019-08-05 |  | 3 | Intro Call - COMM |  |  |  | 2019-08-05 | 2019-08-06 | 2019-08-08
P&L Review - COMM | 246116 - Doubletree Tucson Reid Park - COMM Install | Not Started | [5 empty] | 2019-10-03 |  |  | 2019-09-26 |  |  | Mark Dixon | New | 2019-08-05 |  | 72 | P&L Review - COMM